## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US01 | Study what an LLM is and how it works at a high level (tokens → embeddings → Transformer → attention → next-token prediction) | SHOULD HAVE |  | Kriti Tripathi | 3- Completed
1 | 1 | US02 | Study what a token is and how text is converted into tokens, and why token count matters | SHOULD HAVE |  | Kriti Tripathi | 3- Completed
1 | 1 | US03 | Study the context window and why it matters when processing annual reports (long PDFs cannot be sent entirely to the model) | SHOULD HAVE |  | Kriti Tripathi | 3- Completed
1 | 1 | US04 | Study the Transformer architecture (self-attention, query/key/value, positional information) and why it is important for LLMs | SHOULD HAVE |  | Kriti Tripathi | 3- Completed
1 | 1 | US05 | Study self-attention and how the model decides which tokens are important relative to other tokens | SHOULD HAVE |  | Kriti Tripathi | 3- Completed
1 | 1 | US06 | Study prompting: system/user prompts, instructions, context, examples, constraints, output format, and what makes a good prompt | SHOULD HAVE |  | Kriti Tripathi | 3- Completed
1 | 1 | US07 | Study temperature in an LLM and its effect on randomness/creativity (why financial analysis needs controlled outputs) | SHOULD HAVE |  | Kriti Tripathi | 3- Completed
1 | 1 | US08 | Study hallucinations in LLMs and why they are dangerous in financial applications | SHOULD HAVE |  | Kriti Tripathi | 3- Completed
1 | 1 | US09 | Study how an LLM generates an answer (input → tokens → model → probability distribution → next token → repeat) | SHOULD HAVE |  | Kriti Tripathi | 3- Completed
1 | 1 | US10 | Study LLM limitations and how to reduce them in a financial research system (RAG, citations, structured outputs, tool calling, validation, grounding) | SHOULD HAVE |  | Kriti Tripathi | 3- Completed
2 | 2 | US11 | Study synthetic user research concepts, LLM persona simulation techniques, and behavioral modeling approaches | MUST HAVE | 1 | Kriti Tripathi | 3- Completed
2 | 2 | US12 | Design system architecture, agent roles, persona data model, and experiment workflow | MUST HAVE | 1 | Kriti Tripathi | 3- Completed
2 | 2 | US13 | Develop experiment workspace where users define product description, target audience, and research objectives | MUST HAVE | 1 | Kriti Tripathi | 3- Completed
2 | 2 | US14 | Build Persona Generation Agent that generates diverse synthetic personas (name, age, occupation, personality traits, behavioral patterns, psychological profile) displayed as visual persona cards | MUST HAVE | 1 | Kriti Tripathi | 3- Completed
2 | 2 | US15 | Implement Persona Memory and Consistency Module so each persona keeps consistent attributes, opinions, and conversation context across multi-turn interactions | MUST HAVE | 1 | Kriti Tripathi | 3- Completed
3 | 3 | US16 | Build Survey Mode where the user defines questions and all personas respond simultaneously, displayed side-by-side for comparison | MUST HAVE | 2 | Kriti Tripathi | 3- Completed
3 | 3 | US17 | Validate persona consistency and response realism across multiple question types and product domains | MUST HAVE | 2 | Kriti Tripathi | 3- Completed
3 | 3 | US18 | Test Survey Mode across diverse persona sets and product categories using sample experiment scenarios | MUST HAVE | 2 | Kriti Tripathi | 3- Completed
3 | 3 | US19 | Build Interview Mode, a conversational interface where the selected persona responds in character, keeping memory and behavioral consistency across turns | MUST HAVE | 2 | Kriti Tripathi | 3- Completed
3 | 3 | US20 | Develop Insight Extraction Agent that analyzes survey and interview responses and surfaces recurring themes, sentiment breakdown, agreement patterns, and behavioral trends | MUST HAVE | 2 | Kriti Tripathi | 3- Completed
3 | 3 | US21 | Implement "Would use this product?" scoring aggregated across persona segments, with reasoning per persona group | MUST HAVE | 2 | Kriti Tripathi | 3- Completed
3 | 3 | US22 | Validate insight extraction quality and theme relevance across varied experiment scenarios | MUST HAVE | 2 | Kriti Tripathi | 3- Completed
4 | 4 | US23 | Build Insights and Experiment Results Dashboard showing theme clusters, sentiment breakdown, key persona quotes, and product validation scores visually | MUST HAVE | 3 | Kriti Tripathi | 3- Completed
4 | 4 | US24 | Develop Research Report Generation Module compiling persona profiles, response highlights, insight summary, and validation scoring into a downloadable PDF | MUST HAVE | 3 | Kriti Tripathi | 3- Completed
4 | 4 | US25 | Conduct end-to-end testing across persona generation, both simulation modes, insight extraction, and report generation | MUST HAVE | 3 | Kriti Tripathi | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7