## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US01 | Study what an LLM is and how it works at a high level (tokens → embeddings → Transformer → attention → next-token prediction) | SHOULD HAVE |  | Kriti Tripathi | 3- Completed
1 | 1 | US02 | Study what a token is, how text is converted into tokens, and why token count matters | SHOULD HAVE |  | Kriti Tripathi | 3- Completed
1 | 1 | US03 | Study the context window and why long annual-report PDFs cannot be sent entirely to the model | SHOULD HAVE |  | Kriti Tripathi | 3- Completed
1 | 1 | US04 | Study the Transformer architecture (self-attention, query/key/value, positional information) | SHOULD HAVE |  | Kriti Tripathi | 3- Completed
1 | 1 | US05 | Study self-attention and how the model decides which tokens matter relative to others | SHOULD HAVE |  | Kriti Tripathi | 3- Completed
1 | 1 | US06 | Study prompting: system/user prompts, instructions, context, examples, constraints, output format | SHOULD HAVE |  | Kriti Tripathi | 3- Completed
1 | 1 | US07 | Study temperature in an LLM and why controlled outputs are needed for analysis | SHOULD HAVE |  | Kriti Tripathi | 3- Completed
1 | 1 | US08 | Study hallucinations in LLMs and why they are dangerous in financial applications | SHOULD HAVE |  | Kriti Tripathi | 3- Completed
1 | 1 | US09 | Study how an LLM generates an answer (input → tokens → model → probability distribution → next token → repeat) | SHOULD HAVE |  | Kriti Tripathi | 3- Completed
1 | 1 | US10 | Study LLM limitations and how RAG, citations, structured outputs, tool calling, validation and grounding reduce them | SHOULD HAVE |  | Kriti Tripathi | 3- Completed
2 | 2 | US11 | Study synthetic user research, LLM persona simulation and behavioral modeling; document the analysis (docs/milestone-2-analysis.md) | MUST HAVE | 1 | Kriti Tripathi | 3- Completed
2 | 2 | US12 | Design system architecture, agent roles, persona data model (Pydantic schemas.py) and LangGraph experiment workflow (graph.py, state.py) | MUST HAVE | 1 | Kriti Tripathi | 3- Completed
2 | 2 | US13 | Develop experiment workspace (Streamlit) where users enter product description, target audience and research objectives | MUST HAVE | 1 | Kriti Tripathi | 3- Completed
2 | 2 | US14 | Build Persona Generation Agent (agents/persona_agent.py) with structured output: name, age, occupation, personality traits, behavioral patterns, psychological profile, shown as persona cards | MUST HAVE | 1 | Kriti Tripathi | 3- Completed
2 | 2 | US15 | Implement Persona Memory and Consistency: shared GraphState with MemorySaver checkpointer, and conversation history replay in Interview Mode | MUST HAVE | 1 | Kriti Tripathi | 3- Completed
3 | 3 | US16 | Build Survey Mode: user-defined questions (8 question types), all personas answer concurrently via Survey Execution Agent; side-by-side results in API and React UI | MUST HAVE | 2 | Kriti Tripathi | 3- Completed
3 | 3 | US17 | Validate persona consistency and realism with Consistency Agent (heuristics + LLM check, one regeneration, flagged if still inconsistent) | MUST HAVE | 2 | Kriti Tripathi | 3- Completed
3 | 3 | US18 | Test Survey Mode across diverse persona sets and product categories using sample scenarios (food delivery, fitness, e-commerce, edtech, productivity) | MUST HAVE | 2 | Kriti Tripathi | 3- Completed
3 | 3 | US19 | Build Interview Mode: persistent multi-turn interviews with layered persona memory (PostgreSQL + optional pgvector), windowed history and idempotent messages | MUST HAVE | 2 | Kriti Tripathi | 3- Completed
3 | 3 | US20 | Develop Insight Extraction Agent: themes, sentiment breakdown, agreement patterns, trends, contradictions and outliers; statistics computed in code, theme discovery by LLM | MUST HAVE | 2 | Kriti Tripathi | 3- Completed
3 | 3 | US21 | Implement "Would use this product?" scoring (Product Usage Agent): 0-100 score, decision band and reasoning per persona, aggregated by segment | MUST HAVE | 2 | Kriti Tripathi | 3- Completed
3 | 3 | US22 | Validate insight extraction quality and theme relevance with grounding checks (every persona id returned by the LLM is verified) | MUST HAVE | 2 | Kriti Tripathi | 3- Completed
4 | 4 | US23 | Build Insights and Experiment Results Dashboard (React + TypeScript + Vite): theme clusters, sentiment bar, evidence quotes, adoption meter and segment scores | MUST HAVE | 3 | Kriti Tripathi | 3- Completed
4 | 4 | US24 | Develop Research Report Generation Module (report_generator.py, reportlab): persona profiles, response highlights, insight summary and recommendations as downloadable PDF | MUST HAVE | 3 | Kriti Tripathi | 3- Completed
4 | 4 | US25 | Conduct end-to-end testing across persona generation, Survey and Interview modes, insight extraction, usage scoring and API errors (pytest: 63 passed, 1 skipped) | MUST HAVE | 3 | Kriti Tripathi | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 167 | 15 | 17 | 21 | 16 | 15 | 17 | 18 | 12 | 12 | 6 | 9 | 3 | 3 | 3
SPRINT 1 BACKLOG
US01 | 1 | Study what an LLM is and how it works (tokens, embeddings, Transformer, next-token prediction) | Sep 7th | Sep 7th | Kriti Tripathi | Others | 3- Completed | 4 | Day 1: 4
US02 | 2 | Study tokens and tokenisation; why token count matters | Sep 7th | Sep 8th | Kriti Tripathi | Others | 3- Completed | 4 | Day 1: 2; Day 2: 2
US03 | 3 | Study the context window and why long annual reports cannot be sent whole | Sep 8th | Sep 9th | Kriti Tripathi | Others | 3- Completed | 4 | Day 2: 2; Day 3: 2
US04 | 4 | Study the Transformer architecture (self-attention, Q/K/V, positional information) | Sep 9th | Sep 9th | Kriti Tripathi | Others | 3- Completed | 4 | Day 3: 4
US05 | 5 | Study self-attention and token importance | Sep 9th | Sep 10th | Kriti Tripathi | Others | 3- Completed | 4 | Day 3: 2; Day 4: 2
US06 | 6 | Study prompting: system/user prompts, examples, constraints, output format | Sep 10th | Sep 11th | Kriti Tripathi | Others | 3- Completed | 4 | Day 4: 2; Day 5: 2
US07 | 7 | Study temperature and controlled outputs for analysis | Sep 11th | Sep 11th | Kriti Tripathi | Others | 3- Completed | 4 | Day 5: 4
US08 | 8 | Study hallucinations and why they are dangerous in financial applications | Sep 12th | Sep 13th | Kriti Tripathi | Others | 3- Completed | 4 | Day 6: 2; Day 7: 2
US09 | 9 | Study how an LLM generates an answer (probability distribution, next token) | Sep 13th | Sep 13th | Kriti Tripathi | Others | 3- Completed | 4 | Day 7: 4
US10 | 10 | Study LLM limitations and mitigation with RAG, citations, validation and grounding | Sep 13th | Sep 14th | Kriti Tripathi | Others | 3- Completed | 4 | Day 7: 2; Day 8: 2
SPRINT 2 BACKLOG
US11 | 1 | Study synthetic user research and persona simulation; write analysis (docs/milestone-2-analysis.md) | Sep 15th | Sep 16th | Kriti Tripathi | Others | 3- Completed | 6 | Day 1: 3; Day 2: 3
US12 | 2 | Design architecture, agent roles, persona schema (schemas.py) and LangGraph workflow (graph.py, state.py) | Sep 16th | Sep 17th | Kriti Tripathi | Design | 3- Completed | 8 | Day 2: 4; Day 3: 4
US13 | 3 | Build experiment workspace in Streamlit (product, audience, objectives) | Sep 18th | Sep 20th | Kriti Tripathi | Coding | 3- Completed | 9 | Day 4: 3; Day 5: 3; Day 6: 3
US14 | 4 | Build Persona Generation Agent with structured output and persona cards | Sep 20th | Sep 23rd | Kriti Tripathi | Coding | 3- Completed | 12 | Day 6: 3; Day 7: 3; Day 8: 3; Day 9: 3
US15 | 5 | Implement persona memory/consistency (GraphState + MemorySaver, interview history replay) | Sep 23rd | Sep 25th | Kriti Tripathi | Coding | 3- Completed | 9 | Day 9: 3; Day 10: 3; Day 11: 3
SPRINT 3 BACKLOG
US16 | 1 | Build Survey Mode: question types, concurrent survey execution, side-by-side results | Sep 26th | Sep 28th | Kriti Tripathi | Coding | 3- Completed | 9 | Day 1: 3; Day 2: 3; Day 3: 3
US17 | 2 | Validate persona consistency and realism (Consistency Agent, retry, flagging) | Sep 28th | Sep 29th | Kriti Tripathi | Unit Test | 3- Completed | 6 | Day 3: 3; Day 4: 3
US18 | 3 | Test Survey Mode on sample scenarios across product categories | Sep 30th | Oct 1st | Kriti Tripathi | System Test | 3- Completed | 6 | Day 5: 3; Day 6: 3
US19 | 4 | Build Interview Mode with persistent layered memory and idempotent messages | Oct 1st | Oct 4th | Kriti Tripathi | Coding | 3- Completed | 12 | Day 6: 3; Day 7: 3; Day 8: 3; Day 9: 3
US20 | 5 | Develop Insight Extraction Agent (themes, sentiment, agreement, contradictions) | Oct 4th | Oct 6th | Kriti Tripathi | Coding | 3- Completed | 9 | Day 9: 3; Day 10: 3; Day 11: 3
US21 | 6 | Implement 'Would use this product?' scoring by persona segment | Oct 6th | Oct 7th | Kriti Tripathi | Coding | 3- Completed | 6 | Day 11: 3; Day 12: 3
US22 | 7 | Validate insight extraction quality and grounding across scenarios | Oct 8th | Oct 9th | Kriti Tripathi | Integration Test | 3- Completed | 6 | Day 13: 3; Day 14: 3
SPRINT 4 BACKLOG
US23 | 1 | Build Insights and Results Dashboard in React (themes, sentiment, quotes, adoption meter) | Oct 12th | Oct 15th | Kriti Tripathi | Coding | 3- Completed | 12 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 3
US24 | 2 | Develop Research Report Generation Module (reportlab PDF) | Oct 15th | Oct 17th | Kriti Tripathi | Coding | 3- Completed | 9 | Day 4: 3; Day 5: 3; Day 6: 3
US25 | 3 | End-to-end testing: persona generation, both modes, insights, scoring (63 tests passing) | Oct 18th | Oct 19th | Kriti Tripathi | System Test | 3- Completed | 8 | Day 7: 4; Day 8: 4
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | Sep 10th | Needed clear understanding of LLM concepts (context window, hallucination) before the Q&A | Prepared answers for all 10 LLM topics
2 | Sep 18th | Choosing architecture and keeping persona attributes consistent across turns | Designed LangGraph pipeline with Pydantic structured outputs and persona memory
3 | Oct 5th | LLM returned inconsistent or invalid typed answers; survey jobs lost on restart | Added consistency validation, value normalisation, resume of partial surveys and interview memory
4 | Oct 17th | LLM provider rate limits and unclear errors in the UI | Switched provider to Groq, added clear error toasts, finished dashboard, PDF report and end-to-end tests

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | Sep 7th | Sep 14th | Kriti Tripathi | Start writing short notes for each LLM topic |  | Studying each topic with examples | Prepared for the Sep 10 Q&A
2 | 2 | Sep 15th | Sep 25th | Kriti Tripathi | Build persona agent with structured output | Hard-coding persona fields in prompts | Documenting design decisions | Persona schema and LangGraph workflow finalised
3 | 3 | Sep 26th | Oct 11th | Kriti Tripathi | Add automated tests for each agent | Trusting raw LLM output without validation | Keeping prompts next to their agents | Validation, memory and tests added; all tests pass
4 | 4 | Oct 12th | Oct 19th | Kriti Tripathi | Show errors clearly in the UI | Relying on one LLM provider | Verifying statistics in code, not by the LLM | Dashboard, report and end-to-end testing completed
5
6
7