## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Kriti Tripathi | 2026-10-05 | Survey left in 'running' state after server restart; the in-process job was lost | Sprint 3 | Kriti Tripathi | Logical | Startup sweeper marks interrupted surveys 'partial'; POST /run resumes and redoes only failed cells | 2026-10-05 | Closed | Test: test_restart_recovers_interrupted_survey
2 | Kriti Tripathi | 2026-10-05 | LLM returned out-of-range or wrong-typed values (e.g. rating outside 1-5) that could corrupt survey results | Sprint 3 | Kriti Tripathi | Logical | Added normalisation per question type; invalid value after retries stored as 'failed' cell, not saved | 2026-10-05 | Closed | Test: test_invalid_llm_value_records_failure_not_corruption
3 | Kriti Tripathi | 2026-10-05 | Inconsistent persona answers (AI/meta language, impossible years of experience for age) entered persona memory | Sprint 3 | Kriti Tripathi | Logical | Consistency Agent rejects, regenerates once with feedback, else stores flagged answer and skips memory write | 2026-10-05 | Closed | Test: test_inconsistent_answer_is_flagged_and_not_remembered
4 | Kriti Tripathi | 2026-10-05 | Retried or concurrent interview messages created duplicate turns | Sprint 3 | Kriti Tripathi | Logical | Added clientMessageId idempotency and per-interview lock | 2026-10-05 | Closed | Tests: test_idempotent_message_replay, test_concurrent_duplicates_do_not_duplicate_turns
5 | Kriti Tripathi | 2026-10-05 | Interview prompt grew with every turn and risked exceeding the context window | Sprint 3 | Kriti Tripathi | Maintainability | Limited history to last INTERVIEW_WINDOW_TURNS turns; older facts retrieved from persona memory | 2026-10-05 | Closed | Test: test_context_is_bounded_but_old_facts_survive_via_memory
6 | Kriti Tripathi | 2026-10-05 | Duplicate memories accumulated per persona | Sprint 3 | Kriti Tripathi | Logical | Added de-duplication and cap on stored memories | 2026-10-05 | Closed | Test: test_dedupe_cap_and_lexical_retrieval
7 | Kriti Tripathi | 2026-10-05 | Unhandled errors could leak internals and secrets (API keys) in responses and logs | Sprint 3 | Kriti Tripathi | Standards | Controlled 503/500 error responses and log redaction of secrets | 2026-10-05 | Closed | Tests: test_unhandled_error_does_not_leak_internals, test_logger_redacts_secrets
8 | Kriti Tripathi | 2026-10-05 | Uploaded documents could be unsafe (spoofed type, zip bomb, user filename in path) | Sprint 3 | Kriti Tripathi | Standards | Extension/MIME/magic-byte checks, zip-bomb check, files stored as sha256 names | 2026-10-06 | Closed | Test: test_rejects_bad_files
9 | Kriti Tripathi | 2026-10-16 | Hugging Face Qwen3-8B provider unreliable / rate limited for structured output | Sprint 4 | Kriti Tripathi | Logical | Switched LLM provider to Groq (change confined to llm.py) | 2026-10-17 | Closed | Commit 1cc0cdc
10 | Kriti Tripathi | 2026-10-16 | When LLM key missing or rate-limited, UI could appear empty with no explanation | Sprint 4 | Kriti Tripathi | User Interface | Backend returns typed llm_unavailable/llm_timeout error; frontend shows a toast instead of fake data | 2026-10-17 | Closed | README: LLM provider section

## Sheet2
Logical
User Interface
Maintainability
Standards
Others