## UT
Sl: No: | Test Case Name | Test Procedure | Condition to be tested | Expected Result | Actual Result
1 | test_persona_generation_reuses_milestone2_agent | Call POST /personas/generate | Experiment with product and audience | Personas created by the Milestone 2 Persona Agent and stored | Passed – 5 Oct 2026 (Sprint 3)
2 | test_m2_graph_compiles_and_pipeline_runs | Run Milestone 2 LangGraph pipeline with mocked LLM | Persona → Survey → Response → Insight | Graph compiles and pipeline completes (regression) | Passed – 6 Oct 2026 (Sprint 3)
3 | test_all_personas_answer_all_questions | Run survey on each sample scenario (wait=true) and fetch /results | Every persona, every question; 5 scenarios | All personas answer all questions in order; no failures; personas' answers differ | Passed – 5 Oct 2026 (Sprint 3)
4 | test_food_delivery_persona_differences_and_types | Run food-delivery survey; compare answers of Meera, Mr. Sharma, Aarav | Yes/no, numeric and open-ended questions | Meera says yes and pays more; Mr. Sharma says no; price-sensitive Aarav mentions price | Passed – 5 Oct 2026 (Sprint 3)
5 | test_every_question_type | Run survey with all 8 question types | open_ended, yes_no, single/multiple_choice, rating, likert, numeric, short_answer | Values typed correctly (bool, choice, list, 1-5, number); text types have no typed value | Passed – 5 Oct 2026 (Sprint 3)
6 | test_partial_failure_then_resume_is_idempotent | Force one LLM call to fail, then call /run again | Partial failure | Survey ends partial; resume redoes only failed cell; no duplicate rows | Passed – 5 Oct 2026 (Sprint 3)
7 | test_invalid_llm_value_records_failure_not_corruption | Make LLM return an invalid typed value | Invalid value after retries | Cell stored as failed; no corrupted value | Passed – 5 Oct 2026 (Sprint 3)
8 | test_inconsistent_answer_is_flagged_and_not_remembered | Make validator reject an answer | Inconsistent persona answer | Answer flagged (accepted=false) and not written to memory | Passed – 5 Oct 2026 (Sprint 3)
9 | test_memory_carries_across_turns | Ask 'Do you care about price?' then 'What would make you switch?' | Two interview turns | Second reply remembers price sensitivity; relevant memory stored with turn; history ordered | Passed – 5 Oct 2026 (Sprint 3)
10 | test_context_is_bounded_but_old_facts_survive_via_memory | Set window to 2 turns; run 7 turns | Long interview | Old turn leaves prompt window but price stance is still retrieved from memory | Passed – 5 Oct 2026 (Sprint 3)
11 | test_idempotent_message_replay | Send the same clientMessageId twice | Retried request | No duplicate turn created | Passed – 5 Oct 2026 (Sprint 3)
12 | test_concurrent_duplicates_do_not_duplicate_turns | Send duplicate messages concurrently | Parallel requests | Only one turn stored | Passed – 5 Oct 2026 (Sprint 3)
13 | test_survey_and_interview_share_one_memory_system | Answer in survey, then ask related question in interview | Shared persona memory | Interview reply uses stance learned in survey | Passed – 5 Oct 2026 (Sprint 3)
14 | test_insights_structure_and_grounding | Extract insights for a completed survey | Responses available | Themes, sentiment, agreement, contradictions returned; participant ids verified against real personas | Passed – 5 Oct 2026 (Sprint 3)
15 | test_insights_include_interviews_and_reject_empty | Extract insights with interviews only, then with no data | Interview data / empty experiment | Interviews included; empty experiment rejected with error | Passed – 5 Oct 2026 (Sprint 3)
16 | test_product_usage_scores_reasoning_segments | Run product-usage scoring | Completed experiment | Score 0-100, decision, reasoning per persona; overall and by-segment aggregates | Passed – 5 Oct 2026 (Sprint 3)
17 | test_decision_bands_and_segments | Check decision band and segment classifier | Scores 0-100 | Bands very_unlikely to very_likely mapped correctly; segments assigned | Passed – 5 Oct 2026 (Sprint 3)
18 | test_usage_partial_failure | Force one persona's usage scoring to fail | Partial failure | Other personas scored; failure reported | Passed – 5 Oct 2026 (Sprint 3)
19 | test_accepts_supported_types_and_feeds_context | Upload pdf, docx, txt, csv | Supported file types | Text extracted and added to persona prompt context | Passed – 5 Oct 2026 (Sprint 3)
20 | test_rejects_bad_files | Upload spoofed/oversized/invalid files | Unsafe upload | Rejected with error | Passed – 5 Oct 2026 (Sprint 3)
21 | test_api_key_enforced_when_configured | Call API without and with API key | API_KEY configured | Request without key rejected; with key accepted | Passed – 5 Oct 2026 (Sprint 3)
22 | test_rate_limit | Send requests over per-minute limit | Rate limit configured | Excess requests rejected | Passed – 5 Oct 2026 (Sprint 3)
23 | test_scenarios_list_has_no_fabricated_data_fields | GET /api/scenarios | Sample scenarios for dashboard | Scenario metadata only; no fabricated personas or answers | Passed – 17 Oct 2026 (Sprint 4)
24 | test_scenario_launch_creates_a_real_experiment | POST /api/scenarios/:slug/launch | Sample scenario | Real experiment created and pre-filled | Passed – 17 Oct 2026 (Sprint 4)
25 | test_experiments_list_includes_persona_and_survey_counts | GET /api/experiments | Experiments with personas and surveys | personaCount and surveyCount returned for dashboard cards | Passed – 17 Oct 2026 (Sprint 4)